# Dermaesthetic Super Apps - MVP Development Roadmap

Date: 2026-06-17

Status: Draft - Pending Approval

Approach: Phased Parallel Streams (Approach C)

Deferred: Laundry, Loyalty & Membership

# Executive Summary

| Metric | Value |
| --- | --- |
| Total Features | 14 (11 Phase 1 + 3 Phase 2) |
| Total Sprints | 28 weeks (1 sprint = 1 week) |
| Buffer Weeks | 4 weeks mobile + 2 weeks backend |
| Team | 2 Flutter devs, 2 Fullstack (CMS/BE) |
| Timeline | June 2026 → January 2027 |
| CTO Target | Beat by ~5 months |
| Go-Live | January 2027 |

## Buffer Strategy

Buffer weeks are strategically placed after critical features to handle integration issues, bug fixes, and testing.

| Buffer | Week | Purpose |
| --- | --- | --- |
| BUF-1 | 5 | Auth integration testing, Bug fixes after critical auth flow |
| BUF-2 | 13 | Booking integration testing, Payment flow validation |
| BUF-3 | 23 | Phase 2 integration testing, Cross-feature validation |
| BUF-4 | 27 | Final QA, Regression testing, App store prep validation |
| B-BUF-1 | 9 | Backend integration testing, Bug fixes, API documentation |
| B-BUF-2 | 10 | Backend performance optimization, Security audit |

### Buffer Usage Rules

Buffer weeks are for integration testing and bug fixes, not new features

Buffer weeks can be used for documentation and code reviews

Buffer weeks can be used for performance optimization

Buffer weeks cannot be used for scope expansion

If no issues arise, buffer weeks can be used for technical debt reduction

# Team Allocation

| Role | Count | Responsibility |
| --- | --- | --- |
| Flutter Developer 1 | 1 | Mobile app (Android + iOS) |
| Flutter Developer 2 | 1 | Mobile app (Android + iOS) |
| Fullstack Developer 1 | 1 | Backend APIs + CMS |
| Fullstack Developer 2 | 1 | Backend APIs + CMS |

Critical Path: Mobile development (2 Flutter devs)

Parallel Work: Backend APIs can be built 1-2 weeks ahead of mobile consumption

# Weekly Sprint Plan

## Backend Sprints (Fullstack Devs)

| Sprint | Week | Focus | Deliverables |
| --- | --- | --- | --- |
| B-1 | 1 | Foundation | Project setup, Auth APIs, User model, DB schema |
| B-2 | 2 | Core APIs | Brand, Booking, Promotion APIs |
| B-3 | 3 | Extended APIs | Notification, Profile, Search APIs |
| B-4 | 4 | Domain APIs | Treatment, Clinic, Skin Analysis APIs |
| B-5 | 5 | Phase 2 APIs | Healthy Food, Shop APIs (Cart, Order) |
| B-6 | 6 | Phase 2 APIs | Treatment Transaction, Skin Journey APIs |
| B-7 | 7 | CMS | Dashboard, Content management |
| B-8 | 8 | Polish | Documentation, Optimization, Security |
| B-BUF-1 | 9 | Buffer | Integration testing, Bug fixes, API documentation |
| B-BUF-2 | 10 | Buffer | Performance optimization, Security audit |

## Mobile Sprints (Flutter Devs)

| Sprint | Week | Focus | Deliverables |
| --- | --- | --- | --- |
| M-1 | 3 | Setup & Auth | Flutter project, Login screen, OTP verification |
| M-2 | 4 | Auth Complete | Register, Forgot Password, Onboarding tutorial |
| BUF-1 | 5 | Buffer | Auth integration testing, Bug fixes, Documentation |
| M-3 | 6 | Homepage | Non-login homepage, Logged-in homepage |
| M-4 | 7 | Homepage Complete | Search functionality, Brand carousel |
| M-5 | 8 | Brands | Brand listing, Brand detail |
| M-6 | 9 | Brands Complete | Clinic page, Treatment page |
| M-7 | 10 | Booking (Part 1) | Clinic selection, Treatment selection, Date picker |
| M-8 | 11 | Booking (Part 2) | Time picker, Booking confirmation, Payment |
| M-9 | 12 | Booking Complete | Booking status, Push notifications |
| BUF-2 | 13 | Buffer | Booking integration testing, Payment flow validation, Bug fixes |
| M-10 | 14 | Profile | Profile page, Edit profile, Address management |
| M-11 | 15 | Profile Complete | Change phone, Change password, Face ID, Privacy |
| M-12 | 16 | Promotions | Promotion listing, Promotion detail |
| M-13 | 17 | History & Skin | Booking history, Skin analysis questionnaire |
| M-14 | 18 | Phase 2 Start | Healthy Food listing, Food detail, Food cart |
| M-15 | 19 | Food Complete | Food order, Order tracking |
| M-16 | 20 | Shop | Shop listing, Product detail, Shop cart |
| M-17 | 21 | Shop Complete | Shop order, Order tracking |
| M-18 | 22 | Treatment & Journey | Treatment transaction, Skin journey |
| BUF-3 | 23 | Buffer | Phase 2 integration testing, Cross-feature validation, Bug fixes |
| M-19 | 24 | Polish (Part 1) | UI polish, Animation, Performance |
| M-20 | 25 | Polish (Part 2) | Bug fixes, Edge cases, Accessibility |
| M-21 | 26 | QA & Testing | Integration testing, E2E testing |
| BUF-4 | 27 | Buffer | Final QA, Regression testing, App store prep validation |
| M-22 | 28 | Store Prep | App store assets, Submission, Release |

# Milestones

| Milestone | Date |
| --- | --- |
| Backend APIs Ready | 2026-07-20 |
| Auth Complete | 2026-07-20 |
| Homepage Live | 2026-08-10 |
| Booking + Payment Live | 2026-09-14 |
| Profile + Promotions Live | 2026-10-19 |
| Phase 2 (Food, Shop) Live | 2026-11-23 |
| App Store Submission | 2027-01-04 |

# Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Flutter dev bottleneck | High | Backend APIs ready 1-2 weeks ahead, parallel development |
| Doku payment integration issues | Medium | Early integration testing, Fallback payment method |
| JNE delivery integration issues | Medium | Early API testing, Mock for development |
| App store rejection | Medium | Follow guidelines, Pre-submission review |
| Scope creep | High | Strict MVP scope, Deferred features documented |
| Team burnout | Medium | Realistic sprint loads, Buffer weeks included |
| Buffer week misuse | Medium | Buffer weeks are for integration testing and bug fixes, not new features |
| Integration issues | High | Buffer weeks placed after critical features (Auth, Booking, Phase 2) |
| Timeline slippage | Medium | 4 buffer weeks provide 17% schedule flexibility |
| Backend delays | Medium | Backend has 2 buffer weeks for integration and security testing |