## Slide 1
Dermaesthetic Super Apps
MVP Development Roadmap June 2026 - January 2027

## Slide 2
Executive Summary
14 Features (11 Phase 1 + 3 Phase 2)
28 Weeks Development (1 sprint = 1 week)
4 Buffer Weeks (strategic placement)
Team: 2 Flutter Devs + 2 Fullstack Devs
Timeline: June 2026 → January 2027
CTO Target: Beat by ~5 months
Deferred: Laundry, Loyalty & Membership

## Slide 3
Team Structure
Role | Count | Responsibility
Flutter Developer 1 | 1 | Mobile app (Android + iOS)
Flutter Developer 2 | 1 | Mobile app (Android + iOS)
Fullstack Developer 1 | 1 | Backend APIs + CMS
Fullstack Developer 2 | 1 | Backend APIs + CMS

## Slide 4
Buffer Strategy
Buffer | Week | Purpose
BUF-1 | 5 | Auth integration testing, Bug fixes
BUF-2 | 13 | Booking integration, Payment validation
BUF-3 | 23 | Phase 2 integration, Cross-feature validation
BUF-4 | 27 | Final QA, Regression testing, Store prep
B-BUF | 9-10 | Backend integration, Security audit

## Slide 5
Features Overview (14 Features)
Feature | Priority | Sprint | Weeks
Authentication & Onboarding | P0 | M-1 to M-2 | 3-4
Homepage | P0 | M-3 to M-4 | 6-7
Brand Pages | P0 | M-5 to M-6 | 8-9
Booking Clinic | P0 | M-7 to M-9 | 10-12
Profile Management | P1 | M-10 to M-11 | 14-15
Notifications | P1 | M-9 | 12
Promotions | P1 | M-12 | 16
History | P1 | M-13 | 17
Skin Analysis | P1 | M-13 | 17
Healthy Food | P2 | M-14 to M-15 | 18-19
Shop | P2 | M-16 to M-17 | 20-21
Treatment Transaction | P2 | M-18 | 22
Skin Journey | P2 | M-18 | 22

## Slide 6
Backend Sprints
Sprint | Week | Focus | Deliverables
B-1 | 1 | Foundation | Project setup, Auth APIs, User model, DB schema
B-2 | 2 | Core APIs | Brand, Booking, Promotion APIs
B-3 | 3 | Extended APIs | Notification, Profile, Search APIs
B-4 | 4 | Domain APIs | Treatment, Clinic, Skin Analysis APIs
B-5 | 5 | Phase 2 APIs | Healthy Food, Shop APIs
B-6 | 6 | Phase 2 APIs | Treatment Transaction, Skin Journey APIs
B-7 | 7 | CMS | Dashboard, Content management
B-8 | 8 | Polish | Documentation, Optimization, Security
B-BUF | 9-10 | Buffer | Integration testing, Bug fixes, Security audit

## Slide 7
Mobile Sprints (Part 1)
Sprint | Week | Focus | Deliverables
M-1 | 3 | Setup & Auth | Flutter project, Login screen, OTP verification
M-2 | 4 | Auth Complete | Register, Forgot Password, Onboarding tutorial
BUF-1 | 5 | Buffer | Auth integration testing, Bug fixes
M-3 | 6 | Homepage | Non-login homepage, Logged-in homepage
M-4 | 7 | Homepage Complete | Search functionality, Brand carousel
M-5 | 8 | Brands | Brand listing, Brand detail
M-6 | 9 | Brands Complete | Clinic page, Treatment page
M-7 | 10 | Booking (Part 1) | Clinic selection, Treatment selection, Date picker
M-8 | 11 | Booking (Part 2) | Time picker, Booking confirmation, Payment
M-9 | 12 | Booking Complete | Booking status, Push notifications
BUF-2 | 13 | Buffer | Booking integration testing, Payment validation
M-10 | 14 | Profile | Profile page, Edit profile, Address management

## Slide 8
Mobile Sprints (Part 2)
Sprint | Week | Focus | Deliverables
M-11 | 15 | Profile Complete | Change phone, Change password, Face ID, Privacy
M-12 | 16 | Promotions | Promotion listing, Promotion detail
M-13 | 17 | History & Skin | Booking history, Skin analysis questionnaire
M-14 | 18 | Phase 2 Start | Healthy Food listing, Food detail, Food cart
M-15 | 19 | Food Complete | Food order, Order tracking
M-16 | 20 | Shop | Shop listing, Product detail, Shop cart
M-17 | 21 | Shop Complete | Shop order, Order tracking
M-18 | 22 | Treatment & Journey | Treatment transaction, Skin journey
BUF-3 | 23 | Buffer | Phase 2 integration testing, Cross-feature validation
M-19 | 24 | Polish (Part 1) | UI polish, Animation, Performance
M-20 | 25 | Polish (Part 2) | Bug fixes, Edge cases, Accessibility
M-21 | 26 | QA & Testing | Integration testing, E2E testing
BUF-4 | 27 | Buffer | Final QA, Regression testing, App store prep
M-22 | 28 | Store Prep | App store assets, Submission, Release

## Slide 9
Gantt Chart (Weeks 1-14)
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
B-1: Foundation
B-2: Core APIs
B-3: Extended APIs
B-4: Domain APIs
B-5: Phase 2 APIs
B-6: Phase 2 APIs
B-7: CMS
B-8: Polish
M-1: Setup & Auth
M-2: Auth Complete
BUF-1: Buffer
M-3: Homepage
M-4: Homepage Complete
M-5: Brands
M-6: Brands Complete
M-7: Booking (Part 1)
M-8: Booking (Part 2)
M-9: Booking Complete
BUF-2: Buffer
M-10: Profile
Backend
Mobile
Buffer

## Slide 10
Gantt Chart (Weeks 15-28)
W15
W16
W17
W18
W19
W20
W21
W22
W23
W24
W25
W26
W27
W28
M-11: Profile Complete
M-12: Promotions
M-13: History & Skin
M-14: Phase 2 Start
M-15: Food Complete
M-16: Shop
M-17: Shop Complete
M-18: Treatment & Journey
BUF-3: Buffer
M-19: Polish (Part 1)
M-20: Polish (Part 2)
M-21: QA & Testing
BUF-4: Buffer
M-22: Store Prep
Backend
Mobile
Buffer

## Slide 11
Milestones
Milestone | Date | Week
Backend APIs Ready | 2026-07-20 | 4
Auth Complete | 2026-07-20 | 4
Homepage Live | 2026-08-10 | 7
Booking + Payment Live | 2026-09-14 | 12
Profile + Promotions Live | 2026-10-19 | 17
Phase 2 Live | 2026-11-23 | 22
App Store Submission | 2027-01-04 | 28

## Slide 12
Risk Register
Risk | Impact | Mitigation
Flutter dev bottleneck | High | Backend APIs ready 1-2 weeks ahead
Doku payment issues | Medium | Early integration testing
App store rejection | Medium | Follow guidelines, Pre-submission review
Scope creep | High | Strict MVP scope, Deferred features documented
Team burnout | Medium | Realistic sprint loads, Buffer weeks

## Slide 13
Next Steps
1. Review and approve this roadmap
2. Set up Flutter project structure
3. Set up backend API architecture
4. Begin Sprint B-1: Foundation (June 22)
5. Begin Sprint M-1: Setup & Auth (July 6)
6. Weekly sprint reviews and adjustments

## Slide 14
Thank You
Questions? Contact: Project Team