## MVP Gantt Chart
Dermaesthetic Super Apps - MVP Gantt Chart
Timeline: June 2026 - March 2027 ¦ Team: 2 Flutter Devs + 2 Fullstack Devs
Sprint | Team | Week | Focus | Deliverables | Start Date | End Date | W1 Jun 22 | W2 Jun 29 | W3 Jul 06 | W4 Jul 13 | W5 Jul 20 | W6 Jul 27 | W7 Aug 03 | W8 Aug 10 | W9 Aug 17 | W10 Aug 24 | W11 Aug 31 | W12 Sep 07 | W13 Sep 14 | W14 Sep 21 | W15 Sep 28 | W16 Oct 05 | W17 Oct 12 | W18 Oct 19 | W19 Oct 26 | W20 Nov 02 | W21 Nov 09 | W22 Nov 16 | W23 Nov 23 | W24 Nov 30 | W25 Dec 07 | W26 Dec 14 | W27 Dec 21 | W28 Dec 28 | W29 Jan 04 | W30 Mar 08 | W31 Mar 15 | W32 Mar 22 | W33 Mar 29 | W34 Apr 05
B-1 | Backend | 1 | Foundation | Project setup, Auth APIs, User model, DB schema | 2026-06-22 | 2026-06-28
B-2 | Backend | 2 | Core APIs | Brand, Booking, Promotion APIs | 2026-06-29 | 2026-07-05
B-3 | Backend | 3 | Extended APIs | Notification, Profile, Search APIs | 2026-07-06 | 2026-07-12
B-4 | Backend | 4 | Domain APIs | Treatment, Clinic, Skin Analysis APIs | 2026-07-13 | 2026-07-19
B-5 | Backend | 5 | Phase 2 APIs | Healthy Food, Shop APIs (Cart, Order) | 2026-07-20 | 2026-07-26
B-6 | Backend | 6 | Phase 2 APIs | Treatment Transaction, Skin Journey APIs | 2026-07-27 | 2026-08-02
B-7 | Backend | 7 | CMS | Dashboard, Content management | 2026-08-03 | 2026-08-09
B-8 | Backend | 8 | Polish | Documentation, Optimization, Security | 2026-08-10 | 2026-08-16
B-BUF-1 | Backend | 9 | Buffer | Integration testing, Bug fixes, API documentation | 2026-08-17 | 2026-08-23
B-BUF-2 | Backend | 10 | Buffer | Performance optimization, Security audit | 2026-08-24 | 2026-08-30
M-0 | Mobile | 2 | Foundation | Flutter project setup, State management, Navigation, Theme system, API layer | 2026-06-29 | 2026-07-05
M-1 | Mobile | 4 | Setup & Auth | Login screen, OTP verification, Register, Forgot Password | 2026-07-13 | 2026-07-19
M-1A | Mobile | 6 | User Onboarding | Tutorial app walkthrough, Feature highlights, Skip/replay, First-time UX | 2026-07-27 | 2026-08-02
M-2 | Mobile | 7 | Multi Language | Language selection, EN/ID/JP strings, Locale persistence, Dynamic UI labels | 2026-08-03 | 2026-08-09
M-3 | Mobile | 8 | Homepage | Non-login homepage, Logged-in homepage | 2026-08-10 | 2026-08-16
M-4 | Mobile | 9 | Homepage Complete | Search functionality, Brand carousel | 2026-08-17 | 2026-08-23
M-5 | Mobile | 10 | Brands | Brand listing, Brand detail | 2026-08-24 | 2026-08-30
M-6 | Mobile | 11 | Brands Complete | Clinic page, Treatment page | 2026-08-31 | 2026-09-06
M-7 | Mobile | 12 | Booking (Part 1) | Clinic selection, Treatment selection, Date picker | 2026-09-07 | 2026-09-13
M-8 | Mobile | 13 | Booking (Part 2) | Time picker, Booking confirmation, Payment | 2026-09-14 | 2026-09-20
M-9 | Mobile | 14 | Booking Complete | Booking status, Push notifications | 2026-09-21 | 2026-09-27
BUF-1 | Mobile | 15 | Buffer | Booking integration testing, Payment flow validation, Bug fixes | 2026-09-28 | 2026-10-04
M-10 | Mobile | 16 | Profile | Profile page, Edit profile, Address management | 2026-10-05 | 2026-10-11
M-11 | Mobile | 17 | Profile Complete | Change phone, Change password, Face ID, Privacy | 2026-10-12 | 2026-10-18
BUF-2 | Mobile | 18 | Buffer | Profile integration testing, Auth flow validation, Bug fixes | 2026-10-19 | 2026-10-25
M-12 | Mobile | 19 | Promotions | Promotion listing, Promotion detail | 2026-10-26 | 2026-11-01
M-13 | Mobile | 20 | History & Skin | Booking history, Skin analysis questionnaire, Saved patients in timeline | 2026-11-02 | 2026-11-08
M-14 | Mobile | 21 | Phase 2 Start | Healthy Food listing, Food detail, Food cart | 2026-11-09 | 2026-11-15
M-15 | Mobile | 22 | Food Complete | Food order, Order tracking | 2026-11-16 | 2026-11-22
M-16 | Mobile | 23 | Shop | Shop listing, Product detail, Shop cart | 2026-11-23 | 2026-11-29
M-17 | Mobile | 24 | Shop Complete | Shop order, Order tracking | 2026-11-30 | 2026-12-06
BUF-3 | Mobile | 25 | Buffer | Phase 2 integration testing, Cross-feature validation, Bug fixes | 2026-12-07 | 2026-12-13
M-18 | Mobile | 26 | Treatment & Journey | Treatment transaction, Skin journey, Saved patient records | 2026-12-14 | 2026-12-20
M-19 | Mobile | 27 | Polish (Part 1) | UI polish, Animation, Performance | 2026-12-21 | 2026-12-27
BUF-4 | Mobile | 28 | Buffer | Final QA, Regression testing, App store prep validation | 2026-12-28 | 2027-01-03
M-20 | Mobile | 29 | Polish (Part 2) | Bug fixes, Edge cases, Accessibility | 2027-01-04 | 2027-01-10
M-21 | Mobile | 30 | QA & Testing | Integration testing, E2E testing | 2027-01-11 | 2027-01-17
M-22 | Mobile | 31 | Store Prep | App store assets, Submission, Release | 2027-01-18 | 2027-01-24
M-23 | Mobile | 32 | Store Review | App store review monitoring, Post-submission fixes, Release coordination | 2027-01-25 | 2027-01-31
BUF-5 | Mobile | 33 | Buffer | Store review response, Critical bug fixes, Release go/no-go | 2027-02-01 | 2027-02-07
BUF-6 | Mobile | 34 | Store Review Buffer | Post-review monitoring, Crash analytics, Hotfix readiness, Launch coordination | 2027-02-08 | 2027-02-14
MILESTONES
◆ |  |  |  | Backend APIs Ready | 2026-07-20 | [5 empty] | ◆
◆ |  |  |  | Auth + Onboarding Complete | 2026-08-10 | [9 empty] | ◆
◆ |  |  |  | Homepage Live | 2026-08-24 | [10 empty] | ◆
◆ |  |  |  | Booking + Payment Live | 2026-10-05 | [16 empty] | ◆
◆ |  |  |  | Profile + Promotions Live | 2026-10-26 | [19 empty] | ◆
◆ |  |  |  | Phase 2 (Food, Shop) Live | 2026-12-07 | [25 empty] | ◆
◆ |  |  |  | App Store Submission | 2027-01-25 | [32 empty] | ◆
◆ |  |  |  | Store Review Complete | 2027-02-08 | [34 empty] | ◆
LEGEND
█ | Backend Development
█ | Mobile Development
█ | Buffer Week
◆ | Milestone